## Sheet1
Work Package | -26 | -25 | -24 | -23 | -22 | -21 | -20 | -19 | -18 | -17 | -16 | -15 | -14 | -13 | -12 | -11 | -10 | -9 | -8 | -7 | -6 | -5 | -4 | -3 | -2 | -1 | GO LIVE | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
Project Governance
Comms and Engagement |  |  |  |  | Planning |  |  |  | Initial Comms |  | Delivery
Clinical Update Training | [10 empty] | Planning |  |  |  | Notice Period for Practices | [7 empty] | Delivery
Revision of Materials | [8 empty] | Planning |  |  |  | Sign-off process |  |  |  | Finalisation of Materials
Data Collection and Analysis | [18 empty] | Planning | [7 empty] | (Baseline quantitative measurement point) |  | Delivery | [8 empty] | (Second quantitative measurement point)
Evaluation | [14 empty] | Planning |  |  |  | Data Collection | [20 empty] | Report Write-Up
Building Quality Improvement Capability | [6 empty] | Planning |  |  |  | Recruitment |  |  |  | Delivery of training and coaching through initial PDSA cycle | [11 empty] | Improvement Coaching
Equality Impact Assessment (EIA) |  |  | Completion
Patient and Public Involvement | [6 empty] | Completion |  |  |  | Delivery
Industry Engagement | Options Appraisal and Planning |  |  |  | Delivery
Information Governance | [18 empty] | Completion
Practice Sign-Up | [10 empty] | Delivery
Implementation | [26 empty] | Delivery
(OPTIONAL: Out Patient Readmission Avoidance) | [18 empty] | Planning
(OPTIONAL: New Medicines Service) | [16 empty] | Planning | [5 empty] | Delivery
Note on A2: Assumed that CCG sign off has been confirmed
Note on A4: Assumes 'big bang' approach
Note on A5: Assumes industry sign off required
Note on R5: design and print; uploading web materials and testing; etc
Note on A8: Assumes this capability is not currently available
Note on A14: Assumes 'big bang' although initial pilot and phase roll-out recommended
Note on T15: Delivered as part of Training package